## README
Decidr Code — Feature Tracker
This workbook lists every feature/user story from the Decidr Code project breakdown plus addendum.
Sheets:
• Features — the master list. 64 stories across 15 epics. Add new rows at the bottom.
• Epics — auto-summarized counts and points per epic (formulas auto-update as you edit Features).
How to add a new feature:
1. Go to the Features sheet.
2. Click any cell inside the table, then go to the next blank row — the table will auto-extend.
3. Use ID convention: US-065, US-066, … (or your own scheme like F-001).
4. Pick the Epic ID from existing ones, or add a new epic in the Epics sheet first.
5. Priority and Status have dropdowns; Category does too. You can edit the allowed values via Data → Data Validation.
Color rules:
• Status = Done → green; In Progress → yellow; Blocked → red.
• Priority = Highest → red highlight.
Source files: PROJECT-BREAKDOWN.md (US-001 to US-046) and FEATURE-ADDENDUM.md (US-047 to US-064).

## Features
ID | Epic ID | Epic Name | Sprint | Story / Feature | Description | Story Points | Priority | Status | Category | Owner | Notes
US-001 | EP-01 | Project Foundation | 1 | Monorepo scaffold | All packages share config and can be developed together. | 3 | Highest | Not Started | Infrastructure
US-002 | EP-01 | Project Foundation | 1 | Local PostgreSQL instance | Develop against a real database via Docker. | 2 | Highest | Not Started | Infrastructure
US-003 | EP-01 | Project Foundation | 1 | Git configuration | Generated files are excluded via proper .gitignore. | 1 | High | Not Started | Infrastructure
US-004 | EP-01 | Project Foundation | 1 | Sidecar package scaffold | Node server can be compiled to a binary later. | 2 | Medium | Not Started | Infrastructure
US-005 | EP-01 | Project Foundation | 1 | Hook scripts scaffold | Event system has scripts to execute. | 1 | Medium | Not Started | Infrastructure
US-006 | EP-02 | Core Engine & Database | 1 | TypeScript type definitions | All packages share a single source of truth for data shapes. | 3 | Highest | Not Started | Backend
US-007 | EP-02 | Core Engine & Database | 1 | PostgreSQL schema with relations | Tickets, reasoning, comments, changelogs stored efficiently. | 5 | Highest | Not Started | Backend
US-008 | EP-02 | Core Engine & Database | 1 | Database connection module | All repositories share a single client. | 2 | Highest | Not Started | Backend
US-009 | EP-02 | Core Engine & Database | 1 | Repository classes | Each table has clean CRUD operations. | 8 | Highest | Not Started | Backend
US-010 | EP-02 | Core Engine & Database | 1 | Service classes | Business logic is separated from data access. | 5 | Highest | Not Started | Backend
US-011 | EP-02 | Core Engine & Database | 1 | Hook execution system | Bash scripts fire on events. | 2 | High | Not Started | Backend
US-012 | EP-02 | Core Engine & Database | 1 | Shared constants | Columns, priorities, tags, node types defined once. | 1 | High | Not Started | Backend
US-013 | EP-03 | REST API Server | 2 | REST API for tickets | React app can read and write tickets. | 5 | Highest | Not Started | Backend
US-014 | EP-03 | REST API Server | 2 | Reasoning and stats endpoints | UI can display decision trees and dashboards. | 3 | High | Not Started | Backend
US-015 | EP-03 | REST API Server | 2 | Claude API proxy endpoint | Frontend can trigger ticket processing without exposing API key. | 3 | High | Not Started | Backend
US-016 | EP-03 | REST API Server | 2 | HTTP utility functions | Route handlers stay clean. | 2 | High | Not Started | Backend
US-017 | EP-04 | MCP Server | 2 | MCP tools | Create and manage tickets from inside Cursor / Claude Code. | 8 | Highest | Not Started | Editor Integration
US-018 | EP-04 | MCP Server | 2 | MCP resources | Read current board state and ticket details from editor. | 3 | High | Not Started | Editor Integration
US-019 | EP-04 | MCP Server | 2 | MCP prompts | Analyze tickets and review diffs with pre-built system prompts. | 2 | Medium | Not Started | Editor Integration
US-020 | EP-04 | MCP Server | 2 | Editor config files | MCP connects automatically. | 2 | High | Not Started | Editor Integration
US-021 | EP-05 | File Bridge | 2 | Create tickets via JSON file drop | Use any editor without needing MCP support. | 3 | Medium | Not Started | Editor Integration
US-022 | EP-05 | File Bridge | 2 | Board state written to file | Any tool can read current board. | 2 | Medium | Not Started | Editor Integration
US-023 | EP-06 | Frontend — Shell & Board | 3 | React app shell with navigation | Switch between Board, Hooks, and Stats views. | 5 | Highest | Not Started | Frontend
US-024 | EP-06 | Frontend — Shell & Board | 3 | Layout components | Consistent header, navigation, toolbar. | 3 | Highest | Not Started | Frontend
US-025 | EP-06 | Frontend — Shell & Board | 3 | Kanban board | All tickets organized by status column. | 5 | Highest | Not Started | Frontend
US-026 | EP-06 | Frontend — Shell & Board | 3 | Shared UI components | Badges, tags, avatars are consistent. | 2 | High | Not Started | Frontend
US-027 | EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | Ticket detail modal | View all information about a ticket in one place. | 5 | Highest | Not Started | Frontend
US-028 | EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | Side-by-side diff viewer | See what code Claude changed. | 3 | Highest | Not Started | Frontend
US-029 | EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | Trigger Claude processing from UI | Generate reasoning and diffs. | 3 | Highest | Not Started | Frontend
US-030 | EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | Interactive decision tree | Understand WHY Claude made each choice. | 8 | Highest | Not Started | Frontend
US-031 | EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | Comment thread | Discuss tickets with Claude. | 3 | High | Not Started | Frontend
US-032 | EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | History timeline | See every action taken on a ticket. | 2 | High | Not Started | Frontend
US-033 | EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | Media drop zone | Attach screenshots and GIFs to tickets. | 2 | Low | Not Started | Frontend
US-034 | EP-08 | Frontend — Create & Panels | 4 | Ticket creation modal | Add new tickets with all details. | 5 | Highest | Not Started | Frontend
US-035 | EP-08 | Frontend — Create & Panels | 4 | Hooks log panel | See what events have fired. | 2 | Medium | Not Started | Frontend
US-036 | EP-08 | Frontend — Create & Panels | 4 | Stats dashboard | Project health at a glance. | 3 | Medium | Not Started | Frontend
US-037 | EP-09 | Tauri Desktop Shell | 5 | Native desktop application (Tauri) | Run without a browser. | 5 | Highest | Not Started | Distribution
US-038 | EP-09 | Tauri Desktop Shell | 5 | System tray icon | Minimize to background. | 3 | Medium | Not Started | Distribution
US-039 | EP-09 | Tauri Desktop Shell | 5 | Sidecar build pipeline | Node server compiles to standalone binary. | 3 | High | Not Started | Distribution
US-040 | EP-10 | VS Code / Cursor Extension | 5 | Editor sidebar panel | See the board without leaving the editor. | 5 | High | Not Started | Editor Integration
US-041 | EP-10 | VS Code / Cursor Extension | 5 | Editor commands | Create tickets and trigger processing from command palette. | 3 | High | Not Started | Editor Integration
US-042 | EP-10 | VS Code / Cursor Extension | 5 | Extension API client utility | Extension can talk to the REST server. | 2 | High | Not Started | Editor Integration
US-043 | EP-11 | Interactive Documentation | 6 | Interactive documentation site | Understand architecture, API, and schemas. | 8 | Medium | Not Started | Documentation
US-044 | EP-11 | Interactive Documentation | 6 | Doc content pages for every feature | Comprehensive coverage of all features. | 5 | Medium | Not Started | Documentation
US-045 | EP-12 | Editor Integration & ECC | 6 | everything-claude-code (ECC) integration | Get 13+ agents, 50+ skills, and hooks. | 3 | Low | Not Started | Editor Integration
US-046 | EP-12 | Editor Integration & ECC | 6 | Optimized agent definitions | Tickets route to the right specialist. | 3 | Medium | Not Started | Editor Integration
US-047 | EP-13 | Git Integration & Branch Strategy | 7 | Auto-link branches by naming convention | Git history visible on tickets via DC-XXX/* naming. | 8 | High | Not Started | Git
US-048 | EP-13 | Git Integration & Branch Strategy | 7 | Commit history on Git tab | Track what changed per ticket. | 5 | High | Not Started | Git
US-049 | EP-13 | Git Integration & Branch Strategy | 7 | Git hooks reporting commits and merges | Real-time tracking via post-commit/checkout/merge. | 5 | High | Not Started | Git
US-050 | EP-13 | Git Integration & Branch Strategy | 7 | Auto-move tickets on branch/merge events | Board stays current automatically. | 3 | High | Not Started | Git
US-051 | EP-13 | Git Integration & Branch Strategy | 7 | Story-level sub-branches | DC-XXX/US-YYY/* organizes work within a ticket. | 3 | Medium | Not Started | Git
US-052 | EP-13 | Git Integration & Branch Strategy | 7 | Branch status indicators on cards | See git state at a glance. | 2 | Medium | Not Started | Git
US-053 | EP-13 | Git Integration & Branch Strategy | 7 | MCP tools for branches and git history | Editors can manage git workflow. | 3 | High | Not Started | Git
US-054 | EP-13 | Git Integration & Branch Strategy | 7 | Git hook installer | One-command setup for tracking. | 2 | Medium | Not Started | Git
US-055 | EP-13 | Git Integration & Branch Strategy | 7 | Relevance detection for unlinked commits | 5-tier hierarchy so nothing falls through cracks. | 3 | Medium | Not Started | Git
US-056 | EP-14 | Document Generation | 8 | Export entire project as a document | Complete record of all tickets and work. | 8 | High | Not Started | Export
US-057 | EP-14 | Document Generation | 8 | Choose export format (PDF/MD/HTML/DOCX) | Share in the right format. | 3 | High | Not Started | Export
US-058 | EP-14 | Document Generation | 8 | Export includes reasoning, diffs, comments, git | Comprehensive document content. | 5 | High | Not Started | Export
US-059 | EP-14 | Document Generation | 8 | Export MCP tool | Generate documents from the editor. | 2 | Medium | Not Started | Export
US-060 | EP-15 | Visual Flow Diagrams | 8 | Architecture flow diagram | See how packages connect. | 5 | Medium | Not Started | Visualization
US-061 | EP-15 | Visual Flow Diagrams | 8 | Ticket lifecycle visualization | State machine with hook annotations. | 3 | Medium | Not Started | Visualization
US-062 | EP-15 | Visual Flow Diagrams | 8 | Data flow diagram | Trace requests from UI to database. | 3 | Medium | Not Started | Visualization
US-063 | EP-15 | Visual Flow Diagrams | 8 | Reasoning pipeline visualization | See how tickets get processed. | 3 | Medium | Not Started | Visualization
US-064 | EP-15 | Visual Flow Diagrams | 8 | Mini per-ticket flow | Show each ticket's journey so far. | 2 | Low | Not Started | Visualization

## Epics
Epic ID | Epic Name | Sprint | Story Count | Total Points | Done Count | % Complete
EP-01 | Project Foundation | 1 | 5 | 9 | 0 | 0%
EP-02 | Core Engine & Database | 1 | 7 | 26 | 0 | 0%
EP-03 | REST API Server | 2 | 4 | 13 | 0 | 0%
EP-04 | MCP Server | 2 | 4 | 15 | 0 | 0%
EP-05 | File Bridge | 2 | 2 | 5 | 0 | 0%
EP-06 | Frontend — Shell & Board | 3 | 4 | 15 | 0 | 0%
EP-07 | Frontend — Ticket Detail & Reasoning | 3-4 | 7 | 26 | 0 | 0%
EP-08 | Frontend — Create & Panels | 4 | 3 | 10 | 0 | 0%
EP-09 | Tauri Desktop Shell | 5 | 3 | 11 | 0 | 0%
EP-10 | VS Code / Cursor Extension | 5 | 3 | 10 | 0 | 0%
EP-11 | Interactive Documentation | 6 | 2 | 13 | 0 | 0%
EP-12 | Editor Integration & ECC | 6 | 2 | 6 | 0 | 0%
EP-13 | Git Integration & Branch Strategy | 7 | 9 | 34 | 0 | 0%
EP-14 | Document Generation | 8 | 4 | 18 | 0 | 0%
EP-15 | Visual Flow Diagrams | 8 | 5 | 16 | 0 | 0%
TOTAL |  |  | 64 | 227 | 0 | 0%